## Sheet1
Remarks | Status | Feedback
| Done | 1. Parent category, after defined, is not shown in manage question page which needs to be shown
| Done | 2. Negative Marking: Not required during set creation, rather they will be incorporated while preparing questions
| Done | 3. Randomization: Is application both for set creation and question creation.
| Done | 4. Total marks validation needs to be incorporated
| Done | 5. Once question is created, by default it should be marked as “inactive”. Later will be made active
| Done | 6. Question sequence will be given as the latest one to be at the beginning
| DOne | 7. Question Reject or Decline option should also be incorporated in approval stage
| Done | 8. Search option for question sets needs to be incorporated
| Done | 9. “Allow back button”: The allow back button can be selected
| Done | 10. Time Frame: Exam expiry time can be defined and to be configured
| Done | 11. All forms of print screen/screenshot/copying options need to be disabled from the system
Will be added after UAT | Wishlist | 12. IP and MAC Tracking option to be enabled
| Done | 13. Option to appear the questions in the screen section-wise should be kept
| DOne | 14. QR code should be generated for Admit Card & Question Papers
| Done | 15. Score % to be changed
| DOne | 16. The SMS/email sender for the survey to be made dynamic. Also the templates can be used to invite for survey.
| Not Done for Vendor | 17. Pictures and Signatures for Admit Card will be fetched from Recruitment System
| Done | 18. For answering questions, all MCQ checkbox should be shown similarly, in spite of having one or multiple correct answers
| Done | 19. For hardcopy exams, answer sheets to be downloaded in PDF format only
| Done | 20. Survey should also include approval flow before rolling
| Wishlist | 21. BBL will provide some sample survey templated to be developed in the system
| Wishlist | 22. The criteria to set the order for showing any list will be provided by BBL
| Wishlist | 23. For survey, if any participant does not fill out the survey, that should be escalated to immediate supervisor. The information will be fetched through API from EBS
| DOne | 24. USER Management: User while created will be kept “Inactive” by default
| Done | 25. User Log report will be required to see user activities
| DOne | 26. The System can be accessed through internet. The configuration has been done in QMS
| Done | 27. Dashboard sample screenshot will be shared by Divergent team, based on that we will share our dashboard requirements.
| Done | 28. Candidate ID will automatically be inactive once the exam is completed, this will be done based on requirement
| Done | 29. SMS character limit will be increased to 480 characters
| Done | 30. Survey instructions to be made dynamic
| Wishlist | 31. Scale of 1 to 5 to be incorporated
| Done | 32. For each survey question we can assign certain weight to generate the final result
Will be added after UAT / With CR / Discussion | Wishlist | 33. Anonymous Survey: A declaration Statement to be provided and users can log into the system and chose anonymous to hide user level detail.
| Done | 34. For excel bulk upload template subcategory option to be included
| Done | 35. Excel bulk upload template for candidates should be downloaded with the information already available in the system. Rest of the information will be filled out by the users and uploaded in the system.
| Done | 36. Forget password option to be enabled for specified users
Will be added after UAT / With CR / Discussion | Wishlist | 37. Need to disconnect automatically after 30 minutes of inactivity. Resume from the previous session when log in.
| Done | 38. In the page of changing password give all instruction at once
| Done | 39. After changing the password no need to show the password changing section again.
| Done | 40. Similar name of Parent Category should be restricted.
| Done | 41. Don't have any expiry date option in the time of question creation.
| Done | 42. Mandatory/Not Mandatory: Selecting this field shuold be compulsory.
| Done | 43. 0,-1, d,D this are accepted as question Marks. Field shouldn't accept the value.
| Done | 44. Duplication Check: Same question in a single category should be given notification for duplication.
| Done | 45. After approve a question from pending list(also when using filter) , it goes to the page of MANAGE QUESTIONS. But it should remain on the same page with same filter criteria------>
Will be added after UAT / With CR / Discussion | Wishlist | 46. Need Check/Tick box to select multiple question at once to approve/Pending
| Done | 47. Need unique Serial number for each question
| Done | 48. Wrong answer shows as correct Answer------->
| Done | 49. Only Correct answer should be shown as GREEN color(it can be 2nd, 3rd or 4th option)------->
Will be added after UAT | Wishlist | 50. Duplication Check: Same Answer for a particular question should be given notification for duplication----->
| Done | 51. Need Serial number for each answer to limit/understand the number of total MCQ option------>
| Done | 52. Need Serial number for each question to understand the number of total Question in added list------>
| Done | 53. During the time of preparing question, Question category shows all parent category,sub category in unsorted way. Can't recognize the parent categoty of any sub category----->
| Done | 54. After downloading the question set- name should be as per the question set name..Now it came as OUTPUT
Special Correcter not allowed in PDF | Done | 55. haven’t/ hasn't come as havenâ€™t after download the question set------>
| Done | 56. We can added duplicate or already existed category name in the Category List, but it should be restricted
| Done | 57. Need a creation "Date", Creator's Name in Manage Categories
Already Shared Docs | Done | 58. History for total work flow
| Done | 59. After Adding Question, Edit Question Page appeared instead of Add question Page
| Done | 60. After download the question paper (PDF format), Marks Allocation is not there
| Done | 61. Need marks of all questions after downloading the Questions
| Done | 62. After Downloading the questions- Need catagoty name (Ex: English, Math, Etc)
| Done | 63. Time of question creation - Descriptive Question shows at last but after downloading the question the Descriptive Question comes at the part of MCQ
| Done | 64. Space Need for Descriptive Question
Delete option will not available for any one | Done | 65. User/approver cant delete any qns. Status is only "Approved" or at " Pending" state
question appeared 0 times / total 13 questions appeared overall | Done | 66. What "User Stat" defines from Manage Qns?
| Done | 67. In "Exam" section's "Edit Set" total Marks of Qns needed to be shown
| Done | 68. Need marks of all questions after downloading the Questions
| Done | 69. After Downloading the questions- Need catagoty name (Ex: English, Math, Etc)
| Done | 70. Time of question creation - Descriptive Question shows at last but after downloading the question the Descriptive Question comes at the part of MCQ
| Done | 71. Space Need for Descriptive Question
Delete option will not available for any one | Done | 72. User/approver cant delete any qns. Status is only "Approved" or at " Pending" state
question appeared 0 times / total 13 questions appeared overall | Done | 73. What "User Stat" defines from Manage Qns?
| Done | 74. In "Exam" section's "Edit Set" total Marks of Qns needed to be shown
| Done | 75. Add marks in bulk questions excel format------>
| DOne | 76. Need sub category in bulk questions excel format------>
| Done | 77. Need negative questions & mandatory option in bulk excel format ------>
| Done | 78. After implementation the bulk questions, questions category is not found in “edit question” category------>
| Done | 79. When uploading the bulk question- All MCQ questions uploaded successfully but the descriptive question not uploaded------>
| Done | 80. When uploading the bulk survey questions- It goes to page of Questions & automatically added in Questions Pool, But it should be in survey pool ---->
| Done | 81. As a candidate_ in the time of answering the written exam_restricted the paste option.
Will be added after UAT / With CR / Discussion | Wishlist | 82. As a candidate_ in the time of answering the written exam_restricted the spelling mistake option as view of candidate.
| Done. | 83. Exam type should be MCQ & Written